## Cost Details
Rehab Costs | petty lane
Material/Labor | Where/Who | Date | Actual Cost | Who Paid | Comments
Demo |  |  | 2570 | Kelly |  | 36514.37 |  | Demo Total | 5225 | 2875
Windows | Rock Corps | 2017-08-15 | 1973.71 | Kelly |  | 10365.45 |  | Exterior Siding | 12977.96
Demo | Endura Services | 2017-08-16 | 600 | Kelly |  | 16019.16 |  | Framing subtotal | 5225.07
Windows | Impressive Exteriors | 2017-08-17 | 6950 | Brad | paid in full 9/6/17 |  |  | Exterior Paint Total | 4162.63
Aspestos Check | Abstech | 2017-08-17 | 100 | Brad |  |  |  | Windows Total | 8923.71
*Door Hardware | Amazon | 2017-08-18 | 496.96 | Brad |  |  |  | First Draw Total (9/12/17) | 36514.37
Framing Supplies | Home Depot | 2017-08-30 | 630.04 | Brad |  |  |  |  | 35277
Framing Supplies | Home Depot | 2017-08-22 | 382.81 | Brad |  |  |  |  | ask about fees
*Oleg Babin Invoice(Materials) |  | 2017-08-27 | 1200 | Kelly
Joists Framing Materials | Home Depot | 2017-08-30 | 630.04 | Brad |  |  |  | Electrical | 2382.93
Landscape Cleaning | Rauil Ruiz | 2017-08-27 | 320 | Brad |  |  |  | Second Draw | 8401.09
Paints | Kelly-Moore Paints | 2017-08-30 | 621.93 | Kelly |  |  |  | Permit Fees: | 3254.36
*Architecture Servcies | ALH and Associates | 2017-08-30 | 470 | Kelly
Demo | Endura Services | 2017-08-30 | 1560 | Kelly
Joists Framing Materials | Home Depot | 2017-08-31 | 120.21 | Brad |  |  |  | Permits | 3354.36
Rauil Ruiz | Landscape Cleaning | 2017-08-30 | 175 | Brad
*Electrical | Eric Peterson | 2017-08-31 | 900 | Brad | Paid him 1/2 of electrical work |  |  | Electrical | 1891.09
Toby Bench | Framing | 2018-08-31 | 1500 | Brad |  |  |  | Drywall | 420
Framing Material | Home Depot | 2017-09-04 | 291.46 | Brad |  |  |  | Plubing | 4700
Tom Collins | Reinbursement of Paint | 2017-09-05 | 400 | Brad |  |  |  | Draw 2 | 10365.45 | 6165.45
Tom Collins | Paint, Labor | 2017-09-08 | 3031 | Brad |  |  |  | Brad | 2213.13
Quinn hofmann | Siding, windows | 2017-09-09 | 12977.96 | Kelly |  |  |  | Kelly | 8152.32
*Granite Outlet | Countertops | 2017-08-08 | 2034.02 | Kelly
Home Depot | Framing material | 2017-09-11 | 170.51 | brad |  |  |  | Actual Received: | 9934
Kelly Moore Paint | Deck Stain | 2017-09-11 | 109.7 | Brad
Ceiling Joists | Eric Peterson | 2017-09-13 | 1500 | Brad |  |  |  | Draw 3
Permit Fees | City of Sacramento | 2017-09-13 | 1228.16 | Kelly
Permit Fees | City of Sacramento | 2017-11-20 | 1556.2 | Kelly
Paint Prep | Tom Collins | 2017-10-23 | 120 | Brad
Electrical Supplies | Home Depot | 2017-10-30 | 582.93 | Brad
Paint Prep | Tom Collins | 2017-10-30 | 300 | Brad
Kitchen/Bathroom Cabinets | Cabinets To Go | 2017-10-20 | 6874.74 | Kelly
Plumbing | Don O'Halloran | 2017-11-01 | 4200 | Kelly
Numbers for the house | HD supply | 2017-11-10 | 7.31 | Brad
Hot Mop | Mark Lee | 2017-11-17 | 500 | Kelly
Flooring | German Floor |  | 1906.13 | Kelly | PAID in FULL
Countertops | Granite Outlet |  | 37.89 | Kelly | layout change
Electrical Supplies | Home Depot | 2017-11-05 | 197.96 | Kelly
Electrical Supplies | Home Depot |  | 210.2 | Brad
Duct Work | Glenn Julian | 2017-11-30 | 3500 | Kelly | PAID 1/3/18
Framing | Eric Peterson |  | 1000 | Kelly
Electrical | Eric Peterson |  | 1100 | Kelly
Imperfect Smooth Texture | Miguel |  | 4000 | Kelly
Drywall Material | Brad |  | 800 | Kelly
Drywal Labor | Brad |  | 2000 | n/a
Drywall Fee | Brad |  | 3220 | n/a
Plumbing Prep | two Handy Men |  | 300 | brad
Concrete | Steves Ready Mix |  | 608.78 | Brad
Rock | Capitol Sand |  | 278 | Brad
Concrete Labor | Jeff |  | 2000 | Brad
Subfloor Materials | Home Depot |  | 1800 | Brad
SUbfloor Materials | Home Depot |  | 550 | Brad
Dumpster | Waste Removal |  | 375 | Brad
Tile for shower and fireplace | Floor and Decor |  | 400 | Kelly | Actual $370.18, $400 paid to brad
Tile for shower and fireplace | Floor and Decor |  | 920.25
Plywood for Cabinets | Home Depot |  | 134.7 | Brad
Appliances |  |  | 3186.45 | Kelly
Light fixtures | Home Depot |  | 230 | Brad | Home depot card
Landscaping Drip system | Home Depot |  | 384.21 | Brad
Supplies | Home Depot |  | 145.48 | Brad
Insulation and tile accs | Home Depot |  | 77.02 | Brad
Plywood for Cabinets | Home Depot |  | 356.68 | Brad
Pay jeff to shut up | Jeff |  | 220 | Brad
Tile for 2nd unit and Shower | Floor and Decore |  | 440.34 | Brad
Landscape Plants | Home Depot |  | 603.71 | Brad
Landscape supplies | Home Depot |  | 156.81 | Brad
Landscape Supplies | Home Depot |  | 384.21 | Brad
Landscape Supples | Home Depot |  | 25.93 | Brad
Landscape Supplies | Home Depot |  | 105.86 | Brad
Molding and Trim | Home Depot |  | 1089.69 | Brad
Smoke Alarms and Elec | Home Depot |  | 237.18 | Brad
Return Vents | Home Depot |  | 449.44 | Brad
Wood/Supplies | Home Depot |  | 28.18 | Brad
Landscape Supplies | Home Depot |  | 41.57 | Brad
Landscape Supplies | Home Depot |  | 447.87 | Brad
Electrical Stuff | Home Depot |  | 168.96 | Brad
Landscape | Home Depot |  | 27.94 | Brad
Lumber and Drywall | Home Depot |  | 87.84 | Brad
Landscape | Home Depot |  | 40.8 | Brad
Doors and Trim | Home Depot |  | 629.37 | Brad
Landscape | Home Depot |  | 69.67 | Brad
Landscape | Home Depot |  | 78.87 | Brad
Caulk and Base | Home Depot |  | 75.32 | Brad
Landscape | Home Depot |  | 29.4 | Brad | Landscape Total: | 3888.85
Landscape | Hasties |  | 592 | Kelly | To elijah | 1111.15
Landscape | Hasties |  | 400 | Kelly
Landscape | Home Depot |  | 500
Concrete | Home Depot |  | 113.31 | Brad
Paint | Home Depot |  | 155.68 | Brad
Paint | Home Depot |  | 289.55 | Brad
Baseboard and Lights | Home Depot |  | 435.08 | Brad
Door Hardware and Lights | HD Supply |  | 716.19 | Brad
Petty Bath Hardware | Lowes |  | 261.4 | Brad
Concrete Overlay and Dump | Jeff taxara |  | 300 | Brad
Concrete | Spec West |  | 47.17 | Brad
Electrical Work | Thomas |  | 300 | Brad
Misc | HD Supply |  | 176.77 | Brad
Microwave and Thermostat | Best Buy |  | 419.38 | Brad
Misc | Lowes |  | 160.57 | Brad
Misc | Home Depot |  | 94.74 | Brad
Base and plumbing etc | HD SUpply |  | 178.41 | Brad
Molding, Shelves, door | Home Depot |  | 129.41 | Brad
Glass Deposti | All Cities Glass |  | 500 | Brad
Toilets, Faucets and Misc | Home Depot |  | 1015.09 | Brad
Locks and Misc | HD Supply |  | 127.31 | Brad
T-molds and end caps | Germal Flooring |  | 63.65 | Brad
Lights and drywall supps | Home Depot |  | 35.52 | Brad
Paint Supplies | Home Depot |  | 36.54 | Brad
Plumbing supplies | Home Depot |  | 234.83 | Brad
Paint Supplies | Home Depot |  | 44.4 | Brad
Dishwasher +disposal Hookups etc. | HD Supply |  | 51.47 | Brad
Paint | Home Depot |  | 30.81 | Brad
Lights and misc | HD Supply |  | 183.06 | Brad
Misc | HD Supply |  | 388.43 | Brad
Closet Shelf brackets | Home Depot |  | 20.27 | Brad
Paint | Home Depot |  | 59.37 | Brad
Caulk putty and a lock | Home Depot |  | 51.35 | Brad
Closet Sheving | Home Depot |  | 120.08 | Brad
Cabinet Paint and Trim | Home Depot |  | 33.08 | Brad
HVAC Trim | Lowes |  | 32.3 | Brad
HVAC Trim | Lowes |  | 46.86 | Brad
Electrical and Closet Doors | HD Supply |  | 353.22 | Brad
Misc | HD Supply |  | 167.94 | Brad
Dump Run | Lincoln Landfill |  | 17.5 | Brad
Cleaning Supplies and Glue | HD SUpply |  | 19.24 | Brad |  | Lending Home Reimbursements
Thermostat | Lowes |  | 106.67 | Brad |  | 25205 | 2018-03-22
Misc | Home Depot |  | 202.98 | Brad |  | 12904 | 2018-02-02
Misc | Home Depot |  | 172.73 | Brad |  | 5407 | 2018-01-18
Dump Run | Lincoln Landfill |  | 14 | Brad |  | 12128 | 2017-12-28
Labor Misc | James Murphy |  | 600 | Brad |  | 35277 | 2017-10-03
Mirrors | Home Goods |  | 85.79 | Brad |  | 9648 | 2017-11-27
Baseboards | HD SUpply |  | 205.57 | Brad |  | 100569 | total
Misc Yard work | Jeff Taxara |  | 200 | Brad |  | 7533.22 | Not reimbursed by lending home
Misc | HD Supply |  | 69.6 | Brad
Cabinet Backs | 101 Building Supply |  | 175.15 | Brad
T-molds and end caps | German Flooring |  | 21.66 | Brad
Window washing, dump run and misc | Jeff Taxara |  | 200 | Brad
Concrete Step | Jeff Taxara |  | 260 | Brad
Concrete Material | Spec West |  | 47.71 | Brad | [5 empty] | Profit
Base and pantry etc | James Murphy |  | 800 | Brad | [5 empty] | 108102.22
Landscape Maintenance | Eagleview Landscape |  | 120 | Brad | Brad Total | 44648.84
Misc Handyman | Greg |  | 1200 | Brad* Kelly paid brad 1200 | Kelly | 54687.15
Cleaning service |  |  | 350 | brad |  | `
plumbing | Daniel |  | 1500 | kelly
shower door |  |  | 625.98 | kelly
Repairs and expenses for unfinished work |  |  | ???
Hood Material | HD supply |  | 450.84 | Kelly
Hood Labor |  |  | 700 | Kelly
Doors and weather proofing |  |  | 800 | Kelly
Gate | Jason |  | 200 | Kelly
|  |  | 108102.22 |  | Kelly reimbursed Brad on 5/11/18 | 5000 |  | Kelly Paid Brad Total:
[5 empty] | brad owes $600 for pics |  |  | 33288.47
15000
48288.47
2nd draw |  |  | 9457.29
Third Draw |  |  | 3730.98
|  | Total | 218355.28
To Brad: |  | First Draw | 36514.37 |  | Brad Spent to date | 37699.75
16210.77 | 15592.085 |  | 35277
To Kelly: |  |  | 1237.37
20303.6 | 19684.915 |  | 618.685 |  | Plus Kenneth | 14355
36514.37 |  |  |  |  | Kelly Owes | 14355
Brad minus Kenneth | 29167.75 |  |  |  | Brookwood | 4140.17
Kelly minus Kenneth | 11770.94 |  |  |  | Total | 47694.92 | 33339.92
Financing and Holding Costs
Item | Where/Who | Date | Actual Cost | Who Paid | Comments
Cash to Close |  |  | 20835.05 | Kelly
Cash to Close |  |  |  | Brad | 25000
Water Bill | Carmichael Water District | 2017-11-22 | 76.81 | Kelly
Mortgage Payment | Oct |  | 3022.25 | Kelly
Mortgage Payment | Nov |  | 3022.25 | Kelly
Mortgage Payment | Dec |  | 3022.25 | Kelly
Property Tax | Sac County | 2017-12-01 | 1565.87 | Kelly
Utilities | Nov |  | 253.51 | Kelly
Utilities | Jan |  | 173.27 | Kelly
Utilities | Feb |  | 193.72 | Kelly
Mortgage Payment | Jan |  | 3022.25 | Kelly
Mortgage Payment | Feb |  | 3022.25 | Kelly
SMUD |  | 2018-02-15 | 220.23 | Kelly
Mortgage Payment | March |  | 3022.25 | Kelly
Mortgage Payment | April |  | 3022.25 | Kelly
Mortgage Payment | May |  | 3022.25 | Kelly
Mortgage Payment | June |  | 3022.25 | Kelly
Property Tax |  |  | 1713.88 | Kelly
SMUD |  | 2018-06-03 | 206.82 | Kelly
Water Bill |  | 2018-06-05 | 149.25 | Kelly
Water Bill |  | 2018-04-04 | 119.85 | Kelly
Water Bill |  | 2018-02-05 | 84.2 | Kelly
Water Bill |  | 2017-12-21 | 76.81 | Kelly
Water Bill |  | 2017-11-22 | 76.81 | Kelly
Utilities |  | 2018-05-18 | 173.27 | Kelly
Utilities |  | 2018-06-05 | 178.22 | Kelly
Mortgage Payment | July |  | 3022.25 | Kelly
Mortgage Payment | Aug |  | 3022.25 | Kelly
Mortgage Payment | Sept |  | 3022.25 | Kelly
Mortgage Payment | Oct |  | 3022.25 | Kelly
Mortgage Payment | Nov |  | 3022.25 | Kelly
Lending home Default interest | Dec & Sept | 2018-12-13 | 5952.91 | Kelly
Refianacing costs | Dec | 2018-12-13 | 5890 | Kelly | includes 1.5% fees plus processing fees of 1195 and 495
Property Tax | Dec | 2018-12-13 | 1772.29 | Kelly
Interest payment dec Civic loan |  | 2018-12-13 | 1561.65 | Kelly
Notary |  | 2018-12-13 | 175 | Kelly
Alta |  | 2018-12-13 | 25 | Kelly
Escrow |  | 2018-12-13 | 540 | Kelly
Title Ins |  | 2018-12-13 | 845.6 | Kelly
recording service |  | 2018-12-13 | 18.45 | Kelly
Recording fees |  | 2018-12-13 | 225 | Kelly
Recording fees |  | 2018-12-13 | 95 | Kelly
Recording fees |  | 2018-12-13 | 30 | Kelly
Water Bill | 2019-01-01 |  | 176 | Kelly
Interest payment Fay | Jan |  | 3200 | approx
Interest payment Fay | Feb |  | 3200 | approx
Interest payment Fay | March |  | 3200 | approx
Interest payment Fay | April |  | 3200 | approx
Interest payment Fay | May |  | 3200 | approx
Interest payment Fay | June |  | 3200 | approx
Interest payment Fay | July |  | 3200 | approx
Interest payment Fay | August |  | 3200 | approx
Interest payment Fay | Sept |  | 3390 | approx
Water Bill | August |  | 200 | approx
WATER Bill | August/ Paid in Sept |  | 142
Interest payment Fay | Oct |  | 3390
Interest payment Fay | Nov |  | 3390
Interest payment Fay | Dec |  | 3390
Interest payment Fay | Jan |  | 3390
Interest payment Fay | Feb |  | 3390
SMUD | 1 year |  | 2400
WATER Bill | sep - feb |  | 700
Financing costs total |  |  | 114262.92

## Proforma
Proforma
Item | Amount
Loan Payoff | 437000
Repairs | 30000
Closing Costs | 4951.91
Realtor commissions | 14400 | 3% total
Total Costs | 486351.91
Sale | 480000
$ Received | -6351.91
Loan Payoff to Brad | -28750
Loan Payoff to Mom | -25000
Loan to Chuck | -25000
Loan to Dad | -10000
Total amount invested | 121796.14
Loss | 216898.05
Closing Costs
|  |  | Natural Hazard Disclosure Report to NHD Company 99.00 | 99
|  |  | Signing/Notary Services to SnapDocs 150.00 | 150
|  |  | Final Billing Est to County of Sac Utilities 250.00 | 250
|  |  | Prorata R.E. Taxes, 06/28/19 to 07/01/19, 3 days @ $7.3038 (est.) 21.91 | 21.91
Title Charges
|  |  | Homeowners Policy of Title Insurance to Old Republic Title Company 1,604.00 | 1604
|  |  | Recording Fees 225.00 | 225
|  |  | Affordable Housing Recording Fee to Sacramento County 225.00 | 225
|  |  | County Transfer Tax to County of Sacramento 577.50 | 577
|  |  | Property Taxes | 1800
|  |  | Total | 4951.91

## Color Key
Color Key
Yellow | Draw Requested
Green | Draw Paid
Blue | Not completed yet
Red | Not Paid